## Month 1 — Foundation
The Operator's AI Playbook — 90-Day AI Roadmap
Week | Task | Owner | Status | Dependencies | Notes
Week 1 | Conduct 5-question discovery across departments |  | Not Started
Week 1 | Identify executive sponsor |  | Not Started
Week 1 | Establish AI steering committee |  | Not Started
Week 1 | Complete department readiness assessments |  | Not Started
Week 2 | Map processes to 11 AI primitives |  | Not Started
Week 2 | Score opportunities with signal scorecard |  | Not Started
Week 2 | Review vendor landscape |  | Not Started
Week 2 | Define success metrics |  | Not Started
Week 3 | Select top 3 pilot candidates |  | Not Started
Week 3 | Build business cases for pilots |  | Not Started
Week 3 | Assess build vs buy for each |  | Not Started
Week 3 | Draft data requirements |  | Not Started
Week 4 | Finalize pilot selection |  | Not Started
Week 4 | Secure budget approval |  | Not Started
Week 4 | Assign pilot teams |  | Not Started
Week 4 | Create Month 2 detailed plan |  | Not Started

## Month 2 — Pilot
The Operator's AI Playbook — 90-Day AI Roadmap
Week | Task | Owner | Status | Dependencies | Notes
Week 5 | Kick off Pilot #1 |  | Not Started
Week 5 | Set up development environment |  | Not Started
Week 5 | Establish data pipelines |  | Not Started
Week 5 | Define user acceptance criteria |  | Not Started
Week 6 | Build MVP for Pilot #1 |  | Not Started
Week 6 | Begin user testing |  | Not Started
Week 6 | Kick off Pilot #2 |  | Not Started
Week 6 | Document lessons learned |  | Not Started
Week 7 | Iterate on Pilot #1 feedback |  | Not Started
Week 7 | Build MVP for Pilot #2 |  | Not Started
Week 7 | Conduct mid-pilot review |  | Not Started
Week 7 | Assess scaling requirements |  | Not Started
Week 8 | Complete Pilot #1 UAT |  | Not Started
Week 8 | Iterate on Pilot #2 |  | Not Started
Week 8 | Prepare deployment plan |  | Not Started
Week 8 | Update ROI projections |  | Not Started

## Month 3 — Scale
The Operator's AI Playbook — 90-Day AI Roadmap
Week | Task | Owner | Status | Dependencies | Notes
Week 9 | Deploy Pilot #1 to production |  | Not Started
Week 9 | Complete Pilot #2 UAT |  | Not Started
Week 9 | Begin change management training |  | Not Started
Week 9 | Establish monitoring dashboards |  | Not Started
Week 10 | Deploy Pilot #2 to production |  | Not Started
Week 10 | Identify next wave of opportunities |  | Not Started
Week 10 | Document best practices |  | Not Started
Week 10 | Conduct stakeholder review |  | Not Started
Week 11 | Optimize deployed solutions |  | Not Started
Week 11 | Build scaling roadmap |  | Not Started
Week 11 | Assess organizational readiness for expansion |  | Not Started
Week 11 | Update governance framework |  | Not Started
Week 12 | Executive presentation of results |  | Not Started
Week 12 | Finalize next quarter plan |  | Not Started
Week 12 | Celebrate wins |  | Not Started
Week 12 | Archive lessons learned |  | Not Started

## Summary
The Operator's AI Playbook — 90-Day AI Roadmap
Progress Tracker: | Not Started: |  | In Progress: |  | Complete:
Task | Owner | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Conduct 5-question discovery across departments |  | Not Started | █
Identify executive sponsor |  | Not Started | █
Establish AI steering committee |  | Not Started | █
Complete department readiness assessments |  | Not Started | █
Map processes to 11 AI primitives |  | Not Started |  | █
Score opportunities with signal scorecard |  | Not Started |  | █
Review vendor landscape |  | Not Started |  | █
Define success metrics |  | Not Started |  | █
Select top 3 pilot candidates |  | Not Started |  |  | █
Build business cases for pilots |  | Not Started |  |  | █
Assess build vs buy for each |  | Not Started |  |  | █
Draft data requirements |  | Not Started |  |  | █
Finalize pilot selection |  | Not Started |  |  |  | █
Secure budget approval |  | Not Started |  |  |  | █
Assign pilot teams |  | Not Started |  |  |  | █
Create Month 2 detailed plan |  | Not Started |  |  |  | █
Kick off Pilot #1 |  | Not Started |  |  |  |  | █
Set up development environment |  | Not Started |  |  |  |  | █
Establish data pipelines |  | Not Started |  |  |  |  | █
Define user acceptance criteria |  | Not Started |  |  |  |  | █
Build MVP for Pilot #1 |  | Not Started | [5 empty] | █
Begin user testing |  | Not Started | [5 empty] | █
Kick off Pilot #2 |  | Not Started | [5 empty] | █
Document lessons learned |  | Not Started | [5 empty] | █
Iterate on Pilot #1 feedback |  | Not Started | [6 empty] | █
Build MVP for Pilot #2 |  | Not Started | [6 empty] | █
Conduct mid-pilot review |  | Not Started | [6 empty] | █
Assess scaling requirements |  | Not Started | [6 empty] | █
Complete Pilot #1 UAT |  | Not Started | [7 empty] | █
Iterate on Pilot #2 |  | Not Started | [7 empty] | █
Prepare deployment plan |  | Not Started | [7 empty] | █
Update ROI projections |  | Not Started | [7 empty] | █
Deploy Pilot #1 to production |  | Not Started | [8 empty] | █
Complete Pilot #2 UAT |  | Not Started | [8 empty] | █
Begin change management training |  | Not Started | [8 empty] | █
Establish monitoring dashboards |  | Not Started | [8 empty] | █
Deploy Pilot #2 to production |  | Not Started | [9 empty] | █
Identify next wave of opportunities |  | Not Started | [9 empty] | █
Document best practices |  | Not Started | [9 empty] | █
Conduct stakeholder review |  | Not Started | [9 empty] | █
Optimize deployed solutions |  | Not Started | [10 empty] | █
Build scaling roadmap |  | Not Started | [10 empty] | █
Assess organizational readiness for expansion |  | Not Started | [10 empty] | █
Update governance framework |  | Not Started | [10 empty] | █
Executive presentation of results |  | Not Started | [11 empty] | █
Finalize next quarter plan |  | Not Started | [11 empty] | █
Celebrate wins |  | Not Started | [11 empty] | █
Archive lessons learned |  | Not Started | [11 empty] | █